PLANNING AND DEVELOPMENT

Planning – Zoning – Environmental – Permits & Inspections

PO Box 377                                      Fax:  770-567-2024

70 Gwyn St., Suite A                    Phone:  770-567-2007

Zebulon, GA 30295

“Serving Citizens Responsibly”

Short Term Animal Control Strategy – Year One (Fiscal Year 2013-2014)

I.  Finalize / Adopt Initial Animal Control Ordinance, including:

- Registration Fees for Certain Dangerous Dog Breeds

- Penalties for Lack of Vaccinations

- Resolution to Authorize the County to Collect $5 for Every Rabies Vaccination Occurring in the County

- Dog Restraint Districts in Named Subdivisions Only, with Penalties for Dangerous and Nuisance Dogs

- Prepare Necessary Forms and Citations to Enforce Ordinance

- Fine Revenue to go to Animal Control Budget (Department 91)

- The Ordinance would be limited in scope initially, to address the County’s immediate concerns, and the Ordinance could be expanded in later years as animal control procedures are expanded in the County.

- Target dates:  	Present to Planning Commission on July 11, 2013.

1st Reading, BOC:  July 30, 2013

2nd Reading, BOC:  August 14, 2013

II. Develop Concept Plan for Initial Impoundment Area (Outdoor Facility)

- Scaled, In-house Concept Plan for Minimum Impoundment / Confiscation Facility on County Farm Road Site by July 10, 2013

- County Farm Road Site:  Outdoor Impoundment Area, Prefab Building or Trailer for Indoor Records, Equipment, and Food Storage, Perimeter Fencing, Concrete Slab for Impoundment Area, Body Disposal Area

- Cost Estimates for Above Items by July 10, 2013

- Budget Allocation – Fiscal Year 2013-2014, 2014-2015

III. Finalize Plan for Impoundment, Confiscation, and Euthanization of Dangerous Dogs

- Information on Training Classes and Costs

- Possible Equipment:  Cages (Various Sizes), Protective Apparel, Muzzles, Leashes, Separate Vehicle (?), etc.

- Contracts with Vets for Euthanization and Other Possible Medical Services

IV. Initiate Discussions with Municipalities Concerning Joint Animal Control

- Intergovermental Agreements

- Establishment of County Animal Control Officer as Animal Control Officer for Each Muncipality

- Annual Allotment of Municipalities to County to Provide Animal Control (Including $5 for Rabies Vaccinations Performed Within Municipalities to go to County).